## Jira.csv
Autonomous Traffic Intersection Management
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Assignee | Created | Updated | Last Viewed | Resolved | Due date | Labels | Description | Environment | Watchers | Team Id | Team Name | Parent | Parent key | Parent summary | Status Category Changed
Software/Hardware Interface Handshake | TIP-49 | 10276 | Subtask | Done | TIP | Traffic Intersection project | Ikramul Hassan Sazid | 2026-06-20 10:30 | 2026-07-18 12:46 | 2026-06-20 10:30 | 2026-07-18 12:46 |  |  | Define the memory-mapped registers and interrupt lines connecting the FreeRTOS application to the custom hardware logic. Document the integration workflow (e.g., using Vitis for the cohesive software-to-hardware handoff). |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10273 | TIP-46 | Partitioning Analysis | 2026-07-18 12:46
Arbitration Logic Design and Simulation | TIP-48 | 10275 | Subtask | Done | TIP | Traffic Intersection project | Muhammad Umer Hayat | 2026-06-20 09:59 | 2026-07-18 12:46 | 2026-06-20 10:27 | 2026-07-18 12:46 |  |  | Write the hardware description language (HDL) implementation for the localized traffic arbitration logic. Set up the verification environment using QuestaSim or ModelSim to simulate and validate the RTL timing characteristics before generating the bitstream in Vivado. ¦¦Objective¦¦Design hardware traffic arbitration¦¦ ¦Input¦Scheduling logic¦ ¦Output¦Arbitration model¦ ¦Dependencies¦task 6.1¦ ¦Tools¦ModelSim concepts¦ ¦Risk¦Synchronization mismatch¦ ¦Verification Method¦Simulation¦ |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10273 | TIP-46 | Partitioning Analysis | 2026-07-18 12:46
HW/SW Partitioning | TIP-47 | 10274 | Subtask | Done | TIP | Traffic Intersection project | Nader Yahia | 2026-06-20 09:59 | 2026-07-18 12:46 | 2026-06-20 10:00 | 2026-07-18 12:46 |  |  | Identify execution bottlenecks in the FreeRTOS implementation. Define the exact hardware/software boundary, specifying which components (e.g., raw sensor preprocessing, emergency interrupt handling) will be offloaded to the FPGA logic fabric, targeting a Xilinx Artix-7 architecture. ¦¦Objective¦¦Identify hardware acceleration candidates¦¦ ¦Input¦Timing bottlenecks¦ ¦Output¦Partitioning proposal¦ ¦Dependencies¦completed freeRTOS¦ ¦Tools¦Architecture analysis¦ ¦Risk¦Unrealistic FPGA scope¦ ¦Verification Method¦Feasibility review¦ |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10273 | TIP-46 | Partitioning Analysis | 2026-07-18 12:46
Partitioning Analysis | TIP-46 | 10273 | Story | Done | TIP | Traffic Intersection project | Nader Yahia | 2026-06-20 09:58 | 2026-07-18 12:41 | 2026-07-05 12:14 | 2026-07-18 12:41 | 2026-06-27 |  |  |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10121 | TIP-6 | HW/SW Co-Design | 2026-07-18 12:41
WCET Estimation | TIP-45 | 10240 | Subtask | Done | TIP | Traffic Intersection project | Nader Yahia | 2026-06-15 06:54 | 2026-07-18 12:46 | 2026-06-15 06:58 | 2026-07-18 12:46 |  |  | Instrument the code to measure the Worst-Case Execution Time (WCET) for the most critical paths (e.g., collision avoidance logic). ¦¦Objective¦¦Estimate execution bounds¦¦ ¦Input¦Embedded tasks¦ ¦Output¦WCET report¦ ¦Dependencies¦5.2.2¦ ¦Tools¦Timing instrumentation¦ ¦Risk¦Hidden execution paths¦ ¦Verification Method¦Worst-case testing¦ |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10234 | TIP-39 | Embedded C Implementation | 2026-07-18 12:46
Timing Measurements (Jitter & Latency) | TIP-44 | 10239 | Subtask | Done | TIP | Traffic Intersection project | Ikramul Hassan Sazid | 2026-06-15 06:53 | 2026-07-18 12:46 | 2026-06-15 06:57 | 2026-07-18 12:46 |  |  | Use a logic analyzer or FreeRTOS tracing tools to measure task switching latency and interrupt jitter, ensuring they fall within the tolerances defined in Phase 1. ¦¦Objective¦¦Measure jitter and latency¦¦ ¦Input¦Running implementation¦ ¦Output¦Timing analysis report¦ ¦Dependencies¦Task 5.2.1¦ ¦Tools¦Logic analyzer, FreeRTOS trace¦ ¦Risk¦Inaccurate measurements¦ ¦Verification Method¦Repeated measurements¦ |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10234 | TIP-39 | Embedded C Implementation | 2026-07-18 12:46
Scheduler Implementation | TIP-43 | 10238 | Subtask | Done | TIP | Traffic Intersection project | Ikramul Hassan Sazid | 2026-06-15 06:53 | 2026-07-18 12:46 | 2026-06-15 06:56 | 2026-07-18 12:46 |  |  | Write the embedded C logic for the intersection controller. Map the UPPAAL state transitions directly into the FreeRTOS task loops. ¦¦Objective¦¦Implement scheduling logic¦¦ ¦Input¦Scheduling strategy¦ ¦Output¦Embedded scheduler¦ ¦Dependencies¦Story 5.1¦ ¦Tools¦Embedded C¦ ¦Risk¦Race conditions¦ ¦Verification Method¦Static analysis¦ |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10234 | TIP-39 | Embedded C Implementation | 2026-07-18 12:46
IPC & Synchronization Design | TIP-42 | 10237 | Subtask | Done | TIP | Traffic Intersection project | Ikramul Hassan Sazid | 2026-06-15 06:47 | 2026-07-18 12:47 | 2026-06-15 10:58 | 2026-07-18 12:47 |  |  | Implement the specific FreeRTOS queues, mutexes, and semaphores. Ensure strict mechanisms are in place to prevent priority inversion when the Emergency Task preempts normal traffic. ¦¦Objective¦¦Design queues, semaphores, mutexes¦¦ ¦Input¦Task decomposition¦ ¦Output¦IPC architecture¦ ¦Dependencies¦Task 5.1.1 (Task decomposition)¦ ¦Tools¦FreeRTOS¦ ¦Risk¦Priority inversion¦ ¦Verification Method¦Runtime testing¦ |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10233 | TIP-38 | RTOS Architecture | 2026-07-18 12:47
Task Decomposition | TIP-41 | 10236 | Subtask | Done | TIP | Traffic Intersection project | Ikramul Hassan Sazid | 2026-06-15 06:47 | 2026-07-18 12:47 | 2026-06-20 10:00 | 2026-07-18 12:47 |  |  | Define the specific FreeRTOS task handles, priorities, and stack sizes for the Sensor Task, Scheduler Task, Traffic-Light Task, and Emergency Task based on the EDF/RMS analysis from Epic 3. ¦¦Objective¦¦Define RTOS task structure¦¦ ¦Input¦Architecture¦ ¦Output¦Task model¦ ¦Dependencies¦Phase 2¦ ¦Tools¦FreeRTOS¦ ¦Risk¦Task coupling¦ ¦Verification Method¦Design review¦ *Tasks:* * Sensor task * Scheduler task * Traffic-light task * Monitoring task * Emergency task |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10233 | TIP-38 | RTOS Architecture | 2026-07-18 12:47
Task Decomposition | TIP-40 | 10235 | Task | Done | TIP | Traffic Intersection project | Ikramul Hassan Sazid | 2026-06-15 06:46 | 2026-07-18 12:41 |  | 2026-07-18 12:41 |  |  | ¦¦Objective¦¦define RTOS task structure¦¦ ¦Input¦Architecture¦ ¦Output¦Task model¦ ¦Dependencies¦Phase 2¦ ¦Tools¦FreeRTOS¦ ¦Risk¦Task coupling¦ ¦Verification Method¦Design review¦ |  | Ikramul Hassan Sazid | [5 empty] | 2026-07-18 12:41
Embedded C Implementation | TIP-39 | 10234 | Story | Done | TIP | Traffic Intersection project | Md Mostafizur Rahman | 2026-06-15 06:39 | 2026-07-18 12:41 | 2026-06-15 06:56 | 2026-07-18 12:41 | 2026-06-22 |  | Write the core controller logic and rigorously measure its performance against the required real-time constraints. |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10120 | TIP-5 | Embedded FreeRTOS Implementation | 2026-07-18 12:41
RTOS Architecture | TIP-38 | 10233 | Story | Done | TIP | Traffic Intersection project | Md Mostafizur Rahman | 2026-06-15 06:39 | 2026-07-18 12:41 | 2026-06-20 09:59 | 2026-07-18 12:41 | 2026-06-22 |  | Set up the fundamental skeleton of the RTOS, defining how tasks will run and safely share data. |  |  | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10120 | TIP-5 | Embedded FreeRTOS Implementation | 2026-07-18 12:41
Timing Correctness Verification | TIP-37 | 10200 | Subtask | Done | TIP | Traffic Intersection project | Ikramul Hassan Sazid | 2026-06-01 12:49 | 2026-07-18 12:47 | 2026-06-07 22:02 | 2026-07-18 12:47 |  |  | Verify that maximum wait times and emergency vehicle preemption deadlines are strictly met. |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10195 | TIP-32 | Formal Property Verification | 2026-07-18 12:47
Liveness & Deadlock Verification | TIP-36 | 10199 | Subtask | Done | TIP | Traffic Intersection project | Ikramul Hassan Sazid | 2026-06-01 12:49 | 2026-07-18 12:46 | 2026-06-01 12:49 | 2026-07-18 12:46 |  |  | Verify that the system never freezes (deadlock freedom) and that every waiting vehicle eventually gets to cross (starvation avoidance). |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10195 | TIP-32 | Formal Property Verification | 2026-07-18 12:46
Safety Verification | TIP-35 | 10198 | Subtask | Done | TIP | Traffic Intersection project | Ikramul Hassan Sazid | 2026-06-01 12:48 | 2026-07-18 12:46 | 2026-06-15 06:43 | 2026-07-18 12:46 |  |  | Write and verify queries ensuring catastrophic failures cannot happen (e.g., prove that North-South and East-West lanes can never be green at the same time). |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10195 | TIP-32 | Formal Property Verification | 2026-07-18 12:46
Synchronization Channel Design | TIP-34 | 10197 | Subtask | Done | TIP | Traffic Intersection project | Nader Yahia | 2026-06-01 12:43 | 2026-07-18 12:47 | 2026-06-12 22:18 | 2026-07-18 12:47 |  |  | Define the specific UPPAAL synchronization channels (e.g., {{request_crossing!}}, {{grant_green?}}) that allow the different automata to communicate. ¦¦Objective¦¦Define timed synchronization behavior¦¦ ¦Input¦Timed automata¦ ¦Output¦Channel interaction design¦ ¦Dependencies¦4.1.1¦ ¦Tools¦UPPAAL¦ ¦Risk¦Deadlocks¦ ¦Verification Method¦Reachability analysis¦ |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10194 | TIP-31 | Timed Automata Modeling | 2026-07-18 12:47
Abstract Timed Automata Creation | TIP-33 | 10196 | Subtask | Done | TIP | Traffic Intersection project | Nader Yahia | 2026-06-01 12:43 | 2026-06-09 16:14 | 2026-06-01 12:43 | 2026-06-09 16:14 |  |  | Build the core UPPAAL models for the intersection manager, sensors, and vehicles. Focus on keeping the state space small to avoid verification timeouts. ¦¦Objective¦¦Create formal abstract traffic model¦¦ ¦Input¦State machines¦ ¦Output¦UPPAAL XML model¦ ¦Dependencies¦Phase 2¦ ¦Tools¦UPPAAL¦ ¦Risk¦State explosion¦ ¦Verification Method¦Model sanity checking¦ |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10194 | TIP-31 | Timed Automata Modeling | 2026-06-09 16:14
Formal Property Verification | TIP-32 | 10195 | Story | Done | TIP | Traffic Intersection project | Nader Yahia | 2026-06-01 12:35 | 2026-06-18 16:07 | 2026-06-15 06:43 | 2026-06-18 16:07 | 2026-06-07 |  | Write and execute temporal logic queries (CTL) in UPPAAL to mathematically prove the system meets its safety and timing requirements. |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10119 | TIP-4 | UPPAAL Formal Verification | 2026-06-18 16:07
Timed Automata Modeling | TIP-31 | 10194 | Story | Done | TIP | Traffic Intersection project | Nader Yahia | 2026-06-01 12:34 | 2026-06-12 22:04 | 2026-06-12 22:59 | 2026-06-11 21:40 | 2026-06-14 |  | Translate the UML state machines from Epic 2 into abstract, mathematically rigorous timed automata in UPPAAL |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10119 | TIP-4 | UPPAAL Formal Verification | 2026-06-11 21:40
Emergency Prioritization Strategy | TIP-30 | 10193 | Subtask | Done | TIP | Traffic Intersection project | Nader Yahia | 2026-06-01 12:19 | 2026-06-07 21:00 | 2026-06-01 12:19 | 2026-06-07 21:00 |  |  | Design the specific logic for how an emergency vehicle preempts the standard traffic schedule safely. ¦¦Objective¦¦Compare scheduling determinism¦¦ ¦Input¦Task models¦ ¦Output¦Scheduling comparison report¦ ¦Dependencies¦3.1¦ ¦Tools¦FreeRTOS simulations¦ ¦Risk¦Unrealistic task periods¦ ¦Verification Method¦Response-time analysis¦ |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10189 | TIP-26 | Scheduling Strategy Investigation | 2026-06-07 21:00
RMS vs EDF Analysis | TIP-29 | 10192 | Subtask | Done | TIP | Traffic Intersection project | Ikramul Hassan Sazid | 2026-06-01 12:16 | 2026-06-07 21:01 | 2026-06-15 07:31 | 2026-06-07 21:01 |  |  | Compare Rate Monotonic Scheduling (RMS) and Earliest Deadline First (EDF) for the intersection tasks. Produce a report recommending the best approach for deterministic behavior. ¦¦Objective¦¦Compare scheduling determinism¦¦ ¦Input¦Task models¦ ¦Output¦Scheduling comparison report¦ ¦Dependencies¦3.1¦ ¦Tools¦FreeRTOS simulations¦ ¦Risk¦Unrealistic task periods¦ ¦Verification Method¦Response-time analysis¦ |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10189 | TIP-26 | Scheduling Strategy Investigation | 2026-06-07 21:01
Queue Model Comparison | TIP-28 | 10191 | Subtask | Done | TIP | Traffic Intersection project | Md Mostafizur Rahman | 2026-06-01 12:08 | 2026-06-07 22:02 | 2026-06-15 09:35 | 2026-06-07 22:02 |  |  | h4. Simulate and compare M/M/1, M/D/1, and Priority Queues. Output a comparative analysis report on expected queue lengths and delays ¦¦Objective¦¦Compare queue strategies¦¦ ¦Input¦Arrival models¦ ¦Output¦Comparative queue analysis¦ ¦Dependencies¦Arrival Rate Analysis¦ ¦Tools¦Python simulations¦ ¦Risk¦Incorrect assumptions¦ ¦Verification Method¦Analytical validation¦ |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10188 | TIP-25 | Traffic Queue Modeling | 2026-06-07 22:02
Arrival Rate Analysis | TIP-27 | 10190 | Subtask | Done | TIP | Traffic Intersection project | Muhammad Umer Hayat | 2026-06-01 12:02 | 2026-06-09 12:12 | 2026-06-15 09:35 | 2026-06-09 12:12 |  |  | Define the traffic arrival distributions (λ) using MATLAB or Python based on the operational scenarios from Epic 1. ¦¦*Input*¦¦*Traffic assumptions*¦¦ ¦Objective¦Estimate traffic arrival distributions¦ ¦Output¦λ arrival models¦ ¦Dependencies¦Phase 2¦ ¦Tools¦MATLAB/python¦ ¦Risk¦Unrealistic traffic patterns¦ ¦Verification Method¦Statistical consistency¦ |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10188 | TIP-25 | Traffic Queue Modeling | 2026-06-09 12:12
Scheduling Strategy Investigation | TIP-26 | 10189 | Story | Done | TIP | Traffic Intersection project | Ikramul Hassan Sazid | 2026-06-01 12:01 | 2026-06-07 21:04 | 2026-06-15 07:31 | 2026-06-07 21:04 | 2026-06-07 |  | Determine the real-time scheduling algorithms for the intersection controller and the priority logic for emergency vehicles. |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10118 | TIP-3 | Queuing Theory & Scheduling Analysis | 2026-06-07 21:04
Traffic Queue Modeling | TIP-25 | 10188 | Story | Done | TIP | Traffic Intersection project | Muhammad Umer Hayat | 2026-06-01 12:00 | 2026-06-11 21:39 | 2026-06-15 09:36 | 2026-06-11 21:39 | 2026-06-02 |  | Analyze traffic flow and simulate different queueing models to determine the most efficient way to manage waiting vehicles. |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10118 | TIP-3 | Queuing Theory & Scheduling Analysis | 2026-06-11 21:39
Sequence Diagrams | TIP-24 | 10155 | Subtask | Done | TIP | Traffic Intersection project | Nader Yahia | 2026-05-19 14:58 | 2026-05-25 14:27 | 2026-06-01 14:11 | 2026-05-25 14:27 |  |  | Model the time-ordered message passing between system components. Show the sequence from a vehicle being detected by a sensor, to the scheduler processing it, to the traffic light changing. |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10145 | TIP-19 | Behavioral Modeling | 2026-05-25 14:27
State Machine Design | TIP-23 | 10153 | Subtask | Done | TIP | Traffic Intersection project | Muhammad Umer Hayat | 2026-05-19 14:58 | 2026-06-25 10:42 | 2026-05-19 14:58 | 2026-06-25 10:42 |  |  | Map out the traffic flow behavior for standard operations and edge cases (e.g., what happens step-by-step when an emergency vehicle approaches). |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10145 | TIP-19 | Behavioral Modeling | 2026-06-25 10:42
Activity Diagrams | TIP-22 | 10151 | Subtask | Done | TIP | Traffic Intersection project | Ikramul Hassan Sazid | 2026-05-19 14:57 | 2026-05-31 20:07 | 2026-06-02 08:13 | 2026-05-31 20:07 |  |  | _Description:_ Map out the traffic flow behavior for standard operations and edge cases (e.g., what happens step-by-step when an emergency vehicle approaches). |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10145 | TIP-19 | Behavioral Modeling | 2026-05-31 20:07
Component Decomposition & Interfaces | TIP-21 | 10149 | Subtask | Done | TIP | Traffic Intersection project | Md Mostafizur Rahman | 2026-05-19 14:49 | 2026-06-04 21:20 | 2026-05-23 11:30 | 2026-06-04 21:20 |  |  | Define how the components interact. Map out the exact data interfaces (e.g., what data does the sensor send to the RTOS scheduler?). |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10143 | TIP-18 | Architecture Definition | 2026-06-04 21:20
High-Level System Architecture | TIP-20 | 10147 | Subtask | Done | TIP | Traffic Intersection project | Md Mostafizur Rahman | 2026-05-19 14:48 | 2026-06-04 21:20 | 2026-05-23 11:28 | 2026-06-04 21:20 |  |  | Create a SysML Block Definition Diagram (BDD) or high-level architecture diagram showing the sensor subsystem, scheduler, traffic arbitration unit, and controller. |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10143 | TIP-18 | Architecture Definition | 2026-06-04 21:20
Behavioral Modeling | TIP-19 | 10145 | Story | Done | TIP | Traffic Intersection project | Md Mostafizur Rahman | 2026-05-19 14:47 | 2026-06-06 00:48 | 2026-06-02 01:55 | 2026-06-06 00:48 | 2026-05-31 |  | *Description:* Model the dynamic behavior, workflows, and state transitions of the intersection controller. |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10085 | TIP-2 | System Modeling & Architecture | 2026-06-06 00:48
Architecture Definition | TIP-18 | 10143 | Story | Done | TIP | Traffic Intersection project | Md Mostafizur Rahman | 2026-05-19 14:47 | 2026-06-06 00:48 | 2026-06-06 00:48 | 2026-06-06 00:48 | 2026-05-31 |  | *Description:* Define the structural architecture of the cyber-physical system, mapping out both hardware and software components. |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10085 | TIP-2 | System Modeling & Architecture | 2026-06-06 00:48
Use Case Model | TIP-17 | 10141 | Subtask | Done | TIP | Traffic Intersection project | Nader Yahia | 2026-05-19 14:41 | 2026-05-21 09:06 | 2026-05-20 22:20 | 2026-05-21 09:06 |  |  | Create a UML Use Case diagram mapping the actors identified in 1.1.1 to the requirements in 1.2.1. |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10129 | TIP-11 | Use Case Modeling | 2026-05-21 09:06
Safety & Timing Requirements | TIP-16 | 10139 | Subtask | Done | TIP | Traffic Intersection project | Muhammad Umer Hayat | 2026-05-19 14:35 | 2026-05-31 11:53 | 2026-05-19 14:37 | 2026-05-31 11:53 |  |  | Define strict real-time constraints (e.g., maximum wait time, no conflicting green lights). |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10127 | TIP-10 | Requirements Engineering | 2026-05-31 11:53
Non-Functional Requirements | TIP-15 | 10137 | Subtask | Done | TIP | Traffic Intersection project | Nader Yahia | 2026-05-19 14:35 | 2026-05-21 09:06 | 2026-05-22 08:34 | 2026-05-21 09:06 |  |  | Document constraints like determinism, fault tolerance, and scalability. |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10127 | TIP-10 | Requirements Engineering | 2026-05-21 09:06
Functional Requirements | TIP-14 | 10135 | Subtask | Done | TIP | Traffic Intersection project | Ikramul Hassan Sazid | 2026-05-19 14:35 | 2026-05-23 10:33 | 2026-05-23 10:33 | 2026-05-23 10:33 |  |  | *_Description:_* Document system services (e.g., detecting incoming vehicles, granting access). Use SysML or a requirements matrix. |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10127 | TIP-10 | Requirements Engineering | 2026-05-23 10:33
Operational Scenario Definition | TIP-13 | 10133 | Subtask | Done | TIP | Traffic Intersection project | Md Mostafizur Rahman | 2026-05-19 14:33 | 2026-05-22 12:05 | 2026-05-20 19:14 | 2026-05-22 12:05 |  |  | *_Description_*_:_ Define the specific traffic scenarios the system must handle (e.g., 4-way stop, emergency vehicle approaching, sensor failure). |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10125 | TIP-9 | Stakeholder & Problem Analysis | 2026-05-22 12:05
Stakeholder Identification | TIP-12 | 10131 | Subtask | Done | TIP | Traffic Intersection project | Md Mostafizur Rahman | 2026-05-19 14:32 | 2026-05-22 12:05 | 2026-05-19 14:32 | 2026-05-22 12:05 |  |  | List all entities (e.g., standard vehicles, emergency vehicles, pedestrians, sensors) and system constraints. |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10125 | TIP-9 | Stakeholder & Problem Analysis | 2026-05-22 12:05
Use Case Modeling | TIP-11 | 10129 | Story | Done | TIP | Traffic Intersection project | Md Mostafizur Rahman | 2026-05-19 14:14 | 2026-05-21 09:07 | 2026-05-20 19:16 | 2026-05-21 09:07 | 2026-05-24 |  | *Description:* Create visual models of how external actors interact with the system. |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10084 | TIP-1 | Requirements & System Definition | 2026-05-21 09:07
Requirements Engineering | TIP-10 | 10127 | Story | Done | TIP | Traffic Intersection project | Md Mostafizur Rahman | 2026-05-19 14:13 | 2026-05-30 11:44 | 2026-05-23 10:33 | 2026-05-30 11:44 | 2026-05-22 |  | *Description:* Define the functional, non-functional, safety, and timing requirements for the system. |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10084 | TIP-1 | Requirements & System Definition | 2026-05-30 11:44
Stakeholder & Problem Analysis | TIP-9 | 10125 | Story | Done | TIP | Traffic Intersection project | Md Mostafizur Rahman | 2026-05-19 14:12 | 2026-05-22 12:05 | 2026-07-18 12:55 | 2026-05-22 12:05 | 2026-05-20 |  | *Description:* Identify all interacting entities and define the operational scenarios for the intersection. |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 | 10084 | TIP-1 | Requirements & System Definition | 2026-05-22 12:05
Finalization & Presentation | TIP-8 | 10123 | Epic | Done | TIP | Traffic Intersection project | Md Mostafizur Rahman | 2026-05-19 14:03 | 2026-07-18 12:42 | 2026-07-18 12:42 | 2026-07-18 12:42 |  |  |  |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 |  |  |  | 2026-07-18 12:42
Integration & Validation | TIP-7 | 10122 | Epic | Done | TIP | Traffic Intersection project | Ikramul Hassan Sazid | 2026-05-19 14:03 | 2026-07-18 12:42 | 2026-07-18 12:42 | 2026-07-18 12:42 |  |  |  |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 |  |  |  | 2026-07-18 12:42
HW/SW Co-Design | TIP-6 | 10121 | Epic | Done | TIP | Traffic Intersection project | Nader Yahia | 2026-05-19 14:02 | 2026-07-18 12:42 | 2026-07-18 12:42 | 2026-07-18 12:42 |  |  | Determine which parts of the intersection management system are best suited for software versus dedicated hardware logic. |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 |  |  |  | 2026-07-18 12:42
Embedded FreeRTOS Implementation | TIP-5 | 10120 | Epic | Done | TIP | Traffic Intersection project | Nader Yahia | 2026-05-19 14:02 | 2026-07-18 12:42 | 2026-07-18 12:42 | 2026-07-18 12:42 | 2026-06-22 |  | Translate the verified UPPAAL models and scheduling algorithms into a functional, real-time embedded C application. |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 |  |  |  | 2026-07-18 12:42
UPPAAL Formal Verification | TIP-4 | 10119 | Epic | Done | TIP | Traffic Intersection project | Nader Yahia | 2026-05-19 14:02 | 2026-07-18 12:42 | 2026-07-18 12:42 | 2026-07-18 12:42 | 2026-06-15 |  |  |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 |  |  |  | 2026-07-18 12:42
Queuing Theory & Scheduling Analysis | TIP-3 | 10118 | Epic | Done | TIP | Traffic Intersection project | Nader Yahia | 2026-05-19 14:02 | 2026-07-18 12:42 | 2026-07-18 12:42 | 2026-07-18 12:42 |  |  |  |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 |  |  |  | 2026-07-18 12:42
System Modeling & Architecture | TIP-2 | 10085 | Epic | Done | TIP | Traffic Intersection project | Nader Yahia | 2026-05-19 10:52 | 2026-06-06 00:48 | 2026-06-06 00:48 | 2026-06-06 00:48 | 2026-05-31 |  |  |  | Ikramul Hassan Sazid | [5 empty] | 2026-06-06 00:48
Requirements & System Definition | TIP-1 | 10084 | Epic | Done | TIP | Traffic Intersection project | Nader Yahia | 2026-05-19 10:50 | 2026-07-18 12:42 | 2026-07-18 12:42 | 2026-07-18 12:42 | 2026-05-24 |  | *Purpose:* To develop the high level concept of the work we have to do and formalize it by giving definitions, stakeholders, project scope and creating UML requiremen diagrams and use case diagrams |  | Ikramul Hassan Sazid | 4375df7e-038f-4436-a0c0-a2e86d083487 | RTS summer semester 26 |  |  |  | 2026-07-18 12:42